## Dashboard
Drawing Register
Your live overview. Everything here updates from the Tracker tab: add rows there and watch this page change.
DRAWINGS |  | FOR CONSTRUCTION | AWAITING APPROVAL
4 |  | 2 | 1
SUPERSEDED
0
By status
Status | Count
For information | 1
For approval | 1
For construction | 2
Superseded | 0
Want this connected to everything else?
The spreadsheet is one table. The Notion versions link it to the rest of your work.
Free Notion version | https://www.notion.com/templates/architect-drawing-revision-register
Architecture Firm OS | https://notomantra.gumroad.com/l/architects?utm_source=notomantra.com&utm_medium=tool_page&utm_campaign=drawing-register&utm_content=xlsx

## Tracker
Drawing Register
Sample rows are filled in to show the format: overwrite or delete them. Grey headers calculate on their own. Use the dropdowns where you see them.
NotoMantra · https://www.notomantra.com/free/drawing-register/
Drawing no. | Title | Discipline | Scale | Revision | Status | Issue date | Issued to | Revision note
A-101 | Ground Floor Plan | Architecture | 1:100 | D | For construction | 2026-09-02 | Contractor, client | Kitchen wall moved 300mm
A-201 | North Elevation | Architecture | 1:100 | C | For approval | 2026-09-12 | Client, structural engineer | Window heights revised per client
S-101 | Foundation Plan | Structure | 1:50 | B | For construction | 2026-08-19 | Contractor | Pad footing sizes updated
ID-301 | Kitchen Joinery Details | Interiors | 1:20 | A | For information | 2026-09-15 | Joiner | First issue

## How to use
How to use the Drawing Register Template
A drawing register lists every drawing on a project with its number, title, current revision, status and the date it was issued. It is the single record of which version of each drawing is current, so contractors and consultants never build from a superseded sheet.
Steps
Step 1 | Agree a numbering system before the first issue, for example discipline letter plus number.
Step 2 | Add every drawing to the register the moment it is created, even before issue.
Step 3 | When you issue a revision, update Revision, Status, Issue date and Revision note in the same row.
Step 4 | Mark old drawings Superseded instead of deleting them, so the history stays visible.
Step 5 | Send the register with every drawing issue so everyone checks they have the current revision.
Columns
Column | What goes in it | Example
Drawing no. | Unique drawing number | A-201
Title | What the drawing shows | North Elevation
Discipline | Architecture, Structure, Interiors, MEP | Architecture
Scale | Drawing scale | 1:100
Revision | Current revision letter or number | C
Status | For information, For approval, For construction, Superseded | For approval
Issue date | Date this revision was issued | 2026-09-12
Issued to | Who received it | Client, structural engineer
Revision note | What changed in this revision | Window heights revised per client
Why these columns
Most drawing mistakes on site come from someone using an old revision. The Status column, especially Superseded, and a dated Revision note are what make a register trustworthy.