## Dashboard
FF&E Schedule
Your live overview. Everything here updates from the Tracker tab: add rows there and watch this page change.
ITEMS |  | BUDGET | ORDERED OR LATER
4 |  | 5270 | 2
AT RISK OF ARRIVING LATE
1
By status
Status | Count
Specified | 1
Client approved | 1
Ordered | 1
Delivered | 1
Installed | 0
Want this connected to everything else?
The spreadsheet is one table. The Notion versions link it to the rest of your work.
Free Notion version | https://www.notion.com/templates/ffe-procurement-tracker-for-interior-designers
Interior Design Firm OS | https://notomantra.gumroad.com/l/interior-design-firm?utm_source=notomantra.com&utm_medium=tool_page&utm_campaign=ffe-schedule&utm_content=xlsx

## Tracker
FF&E Schedule
Sample rows are filled in to show the format: overwrite or delete them. Grey headers calculate on their own. Use the dropdowns where you see them.
NotoMantra · https://www.notomantra.com/free/ffe-schedule/
Item code | Room | Item | Vendor | Qty | Unit cost | Total | Lead time (weeks) | Status | Install date
LR-03 | Living room | Linen sectional sofa, oat | Local upholsterer | 1 | 2400 | 2400 | 10 | Ordered | 2026-12-01
LR-07 | Living room | Brass pendant cluster | Lighting supplier | 1 | 860 | 860 | 6 | Client approved | 2026-12-01
KT-02 | Kitchen | Counter stools, walnut | Furniture showroom | 3 | 310 | 930 | 4 | Delivered | 2026-11-20
BD-01 | Primary bedroom | Custom linen drapery | Workroom | 2 | 540 | 1080 | 12 | Specified | 2026-12-05

## How to use
How to use the FF&E Schedule Template
An FF&E schedule lists every piece of furniture, fixture and equipment specified for a project, organised by room, with its vendor, quantity, cost, lead time and order status. Interior designers use it to get client approval, place orders, and make sure everything arrives before installation.
Steps
Step 1 | List items room by room during design, even before choosing vendors.
Step 2 | Get client approval on the schedule before ordering, and record it in Status.
Step 3 | Check Lead time against Install date. Anything that cannot arrive in time needs an alternative now.
Step 4 | Update Status as orders move, and note any backorders straight away.
Step 5 | Use the totals as your budget check before and after ordering.
Columns
Column | What goes in it | Example
Item code | Your reference | LR-03
Room | Where it goes | Living room
Item | Name and description | Linen sectional sofa, oat
Vendor | Supplier | Local upholsterer
Qty | Quantity | 1
Unit cost | Cost per item | 2,400
Total | Qty x unit cost (calculated) | 2,400
Lead time (weeks) | Weeks from order to delivery | 10
Status | Specified, Client approved, Ordered, Delivered, Installed | Ordered
Install date | Planned installation | 2026-12-01
Why these columns
The most common FF&E problem is not cost but timing: a sofa with a 12-week lead time ordered 8 weeks before install. Putting Lead time next to Install date and Status makes that risk visible.