## Dashboard
Game Design Document
Your live overview. Everything here updates from the Tracker tab: add rows there and watch this page change.
DESIGN ELEMENTS |  | MUST HAVES | DONE
4 |  | 3 | 1
MUST HAVES DONE
33.33%
By status
Status | Count
Idea | 0
Designed | 1
Building | 1
In playtest | 1
Done | 1
Want this connected to everything else?
The spreadsheet is one table. The Notion versions link it to the rest of your work.
Free Notion version | https://www.notion.com/templates/game-design-doc-for-indie-devs
Indie Game Developer OS | https://notomantra.gumroad.com/l/game_dev_os?utm_source=notomantra.com&utm_medium=tool_page&utm_campaign=game-design-document&utm_content=xlsx

## Tracker
Game Design Document
Sample rows are filled in to show the format: overwrite or delete them. Grey headers calculate on their own. Use the dropdowns where you see them.
NotoMantra · https://www.notomantra.com/free/game-design-document/
Element | Type | Description | Why it exists | Priority | Status | Milestone | Open questions
Dash | Mechanic | Short burst of speed with 0.2s invincibility | Lets skilled players skip damage | Must have | In playtest | Vertical slice | Is the cooldown too short?
Sunken Library | Level | Flooded archive, water rises every 60s | Teaches dash under time pressure | Must have | Building | Vertical slice | Too hard as level 2?
Ink Wraith | Enemy | Teleports behind the player after 3 hits | Punishes standing still | Should have | Designed | Alpha
Pause menu | UI | Resume, settings, quit, controls | Basic usability | Must have | Done | Vertical slice

## How to use
How to use the Game Design Document Template
A game design document, or GDD, describes what a game is and how it works: its core loop, mechanics, levels, characters, controls and interface. For indie developers it works best as a living list of design elements with status and priority, updated as the game changes, rather than a long document written once.
Steps
Step 1 | Write your core loop in one sentence at the top, then add only elements that serve it.
Step 2 | Mark Priority honestly. Most indie games ship late because too many elements are Must have.
Step 3 | Assign each element to a Milestone so scope is visible per build.
Step 4 | Move Status as you work, and keep Open questions for playtests.
Step 5 | Before each milestone, filter by Priority and cut the Nice to haves that are not started.
Columns
Column | What goes in it | Example
Element | Name of the design element | Dash
Type | Mechanic, Level, Character, Enemy, UI, Quest, Audio | Mechanic
Description | What it does, in one or two lines | Short burst of speed with 0.2s invincibility
Why it exists | What it adds to the core loop | Lets skilled players skip damage
Priority | Must have, Should have, Nice to have | Must have
Status | Idea, Designed, Building, In playtest, Done | In playtest
Milestone | Which build it belongs to | Vertical slice
Open questions | What playtesting needs to answer | Is the cooldown too short?
Why these columns
Long written GDDs go stale within weeks. A list of elements with Priority, Status and Milestone stays current, and the Why it exists column stops features that do not serve the core loop.